## Sheet1
Losing Facility | Gaining Facility | Miles | Notice of Intent | Date of Initial Findings | Notice of Public Meeting | Public Meeting Date | Public Comment Summary | Final MPFR | Notice to not Implement | Implemented? | Losing Facility Becoming an LPC
Updated January 31, 2024 (click date to go to MPFR webpage)
Abilene, TX P&DC | North Texas, TX P&DC | 179 | 2024-01-10 | [8 empty] | APPROVED AND MOVING FORWARD
Augusta, GA P&DC | Atlanta, GA RPDC | 167 | 2023-07-12 | 2023-08-01 | 2023-07-24 | 2024-08-09 | 2023-08-09 | 2023-08-24 |  | Y | YES
Bemidji, MN P&DC | Fargo, ND P&DC | 140 | 2024-01-10
Bismarck, ND P&DC | Fargo, ND P&DC | 195 | 2023-11-08 | 2023-11-29 | 2023-11-21 | 2023-12-07 |  |  |  |  | YES | UNDER REVIEW-AWAITING FINAL MPFR
Brockton, MA P&DC | Providence, RI P&DC | 35 | 2024-01-10
Buffalo, NY P&DC | Rochester, NY P&DC | 71.5 | 2023-11-22 | 2024-01-30 | 2024-01-16 | 2024-01-31 |  |  |  |  | YES
Burlington, VT P&DC | Hartford, CT P&DC | 233 | 2024-01-10 | [8 empty] | NO CHANGE-MPFR NOT IMPLEMENTED
Casper, WY P&DC | Billings, MT P&DC | 280 | 2024-01-10
Champaign, IL P&DC | South Suburban, IL P&DC Chicago South, IL RPDC | 127 140 | 2024-01-10
Charleston, SC P&DC | Columbia, SC P&DC | 98.7 | 2024-01-10 | [8 empty] | CANCELED NO MOVES
Charleston, WV P&DC | Pittsburgh, PA P&DC Pennwood Place, PA P&DC | 236 247 | 2023-11-22 | 2024-01-31 | 2024-01-12 | 2024-01-30 |  |  |  |  | YES
Chattanooga, TN P&DC | Music City, TN Annex | 138 | 2023-10-25 | 2023-11-21 | 2023-11-13 | 2023-11-28 |  |  |  |  | YES
Cheyenne, WY P&DC | Denver, CO P&DC | 103 | 2023-11-08 | 2023-11-29 | 2023-11-21 | 2023-12-12 |  |  |  |  | YES | POSTPONED
Columbia, MO P&DC | St. Louis, MO P&DC | 127 | 2023-10-18 | 2023-11-07 | 2023-10-30 | 2023-11-16 |  |  |  |  | YES
Corpus Christi, TX P&DC | San Antonio, TX P&DC | 149 | 2024-01-10 |  | 2024-01-22 | 2024-02-15 |  |  |  |  | YES
Dakota Central, SD P&DC | Fargo, ND P&DC | 236 | 2023-11-08 | 2023-11-29 | 2023-11-21 | 2023-12-08 |  |  |  |  | YES
Eastern Maine, ME P&DC | Southern Maine, ME P&DC | 134 | 2023-11-22 | 2024-01-30 | 2024-01-12 | 2024-02-02 |  |  |  |  | YES
El Paso, TX P&DC | Albuquerque, NM P&DC | 274 | 2023-10-25 | 2023-11-21 | 2023-11-13 | 2023-11-28 |  |  |  |  | YES
Eugene, OR P&DC | Portland, OR RPDC | 120 | 2023-07-12 | 2023-08-01 | 2023-07-24 | 2023-08-08 | 2023-08-08 | 2023-08-24 |  | Y | YES
Fort Myers, FL P&DC | Tampa, FL P&DC Ybor City, FL P&DC | 139 135 | 2023-11-22 | 2024-01-30 | 2024-01-16 | 2023-02-06 |  |  |  |  | YES
Fort Wayne, IN P&DC | Indianapolis, IN RPDC | 124 | 2023-10-25 | 2023-11-21 | 2023-11-13 | 2023-11-29 |  |  |  |  | YES
Fresno, CA P&DC | Sacromento, CA P&DC | 173 | 2024-01-10 |  | 2024-01-22 | 2024-02-14
Grand Forks, ND P&DC | Fargo, ND P&DC | 76.2 | 2023-11-08 | 2023-11-29 | 2023-11-21 | 2023-12-06 |  |  |  |  | YES
Grand Junction, CO P&DC | Denver, CO P&DC | 252 | 2024-01-10
Greenville, SC P&DC | Charlotte, NC RPDC Charlotte, NC LPC | 81.4 93.3 | 2023-09-27 | 2023-10-25 | 2023-10-17 | 2023-11-01 | 2023-11-01 | 2023-12-01 |  | Y | YES
Gulfport, MS P&DC | Jackson, MS P&DC | 160 | 2024-01-10
Iron Mountain, MI P&DC | Green Bay, WI P&DC | 97.7 | 2024-01-10 |  | 2024-01-22 | 2024-02-08
Johnstown, PA P&DC | Pittsburgh, PA P&DC | 78.1 | 2024-01-10 |  | 2024-01-22 | 2024-02-08
Knoxville, TN P&DC | Louisville, KY P&DC | 245 | 2023-10-25 | 2023-11-21 | 2023-11-13 | 2024-11-30 |  |  |  |  | YES
Lehigh Valley, PA P&DC | Harrisburg, PA P&DC | 84.2 | 2023-10-18 | 2023-11-21 | 2023-10-30 | 2024-11-30 |  |  |  |  | YES
Lubbock, TX P&DC | Amarillo, TX P&DC | 122 | 2023-11-22 | 2024-01-30 | 2024-01-12 | 2024-01-31 |  |  |  |  | YES
Macon, GA P&DC | Atlanta, GA RPDC | 87 | 2023-07-12 | 2023-08-01 | 2023-07-24 | 2024-08-08 | 2023-08-08 | 2023-08-24 |  | Y | YES
Manchester, NH P&DC | Boston, MA P&DC Southern, ME P&DC | 50.8 93.1 | 2024-01-10 |  | 2024-01-22 | 2024-02-08
Mcallen, TX P&DC | San Antonio, TX P&DC | 244 | 2024-01-10
Medord, OR P&DC | Portland, OR RPDC | 280 | 2023-07-12 | 2023-08-01 | 2023-07-24 | 2023-08-09 | 2023-08-09 | 2023-08-24 |  | Y | YES
Midland, TX P&DC | Amarillo, TX P&DC | 251 | 2024-01-10
Minneapolis, MN P&DC | St. Paul, MN P&DC | 16.2 | 2023-09-27 | 2023-10-25 | 2023-10-17 | 2023-11-01 | 11/12023 | 2023-12-01 |  | Y | YES
Missoula, MT P&DC | Spokane, WA P&DC | 204 | 2024-01-10
North Platte, NE P&DC | Denver, CO P&DC | 259 | 2024-01-10
Northwest Arkansas, AR P&DC | Oklahoma City, OK P&DC | 227 | 2023-11-08 | 2023-11-29 | 2023-11-21 | 2023-12-06 |  |  |  |  | YES
Peoria, IL P&DC | South Suburban, IL P&DC | 157 | 2024-01-10
Provo, UT P&DC | Salt Lake City, UT ASF | 44.6 | 2023-09-27 | 2023-10-25 | 2023-10-17 | 2023-11-02 | 2023-11-02 | 2023-11-14 |  | Y | YES
Quad Citites, Il P&DC | Des Moines, IA P&DC | 176 | 2024-01-10 | 2024-01-30 | 2024-01-22 | 2024-02-06 |  |  |  |  | YES
Raleigh, NC P&DC | Greensboro, NC RPDC | 81 | 2024-01-10 |  | 2024-01-22 | 2024-02-13
Reno, NV P&DC | Sacromento, CA P&DC | 142 | 2024-01-10 |  | 2024-01-29 | 2024-02-13 |  |  |  |  | YES
Santa Barbara, CA P&DC | Santa Clarita, CA P&DC | 81.6 | 2024-01-10
Sioux Falls, SD P&DC | Omaha, NE P&DC | 186 | 2024-01-10
SO Jersey, NJ P&DC | Philadelphia, PA P&DC | 11.8 | 2024-01-10
South Suburban, IL P&DC | Chicago South, IL RPDC | 10.4 | 2023-09-27 | 2023-10-25 | 2023-10-17 | 2023-11-01 | 2023-11-01 | 2023-11-17 | 2024-01-10 | N | NO CHANGE
Springfield, IL P&DC | St. Louis, MO P&DC | 99.4 | 2024-01-10
Tacoma, WA P&DC | Seattle, WA P&DC | 27.5 | 2023-10-25 | 2023-11-21 | 2023-11-13 | 2023-11-28 |  |  |  |  | YES
Tallahassee, FL P&DC | Jacksonville, FL NDC | 162 | 2023-10-18 | 2023-11-07 | 2023-10-30 | 2023-11-14 |  |  |  |  | YES
Trenton, NJ P&DC | Philadelphia, PA P&DC | 26.4 | 2023-09-27 | 2023-10-25 | 2023-10-17 | 2023-11-02 | 2023-11-02 | 2023-12-01 |  | Y | YES
Tulsa, OK P&DC | Oklahoma City, OK P&DC | 114 | 2024-01-10
Waterloo, IA P&DC | Des Moines, IA P&DC | 128 | 2024-01-10
Wenatchee, WA P&DF | Spokane, WA P&DC | 171 | 2023-10-25 | 2023-11-21 | 2023-11-13 | 2023-11-29 |  |  |  |  | YES
White River Junc, VT P&DC | Hartford, CT P&DC | 144 | 2024-01-10
Wilmington, DE P&DC | Philadelphia, PA P&DC | 29.6 | 2023-10-18 | 2023-11-21 | 2023-10-30 | 2023-11-29 |  |  |  |  | YES
Yakima, WA P&DC | Seattle, WA P&DC | 153 | 2024-01-10